MODULA USA

WMS / ERP Integration AI Agent — Phase 1 Detail Schedule

Weeks 1–4  |  File-Based Integration (CSV / XML / JSON)  |  Full-Time (40 hrs/week)

Phase 1 Goal By end of Week 4, the intern will have built a working file-based integration generator: given a sample CSV, XML, or JSON file from a customer ERP, the agent will parse it, suggest Modula WMS field mappings with LLM assistance, accept confirmation from the user, and generate a tested transformation script ready for deployment.

# Week 1 — Onboarding & Architecture  (Hrs 1–40)

The intern gets oriented, understands the domain, and produces a signed-off architecture before writing a single line of production code. The architecture decision made this week governs every subsequent module.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 1 | 8 hrs | Environment & Orientation | - Workstation setup: Python 3.11, VS Code, Git, pyodbc, venv - Clone project repo (or initialize with agreed structure) - Install and verify: requests, pydantic, lxml, pandas, python-dotenv - Receive and review the Modula WMS Data Dictionary (supervisor provides) - Read 3 provided real anonymized integration examples — note field names, formats, quirks - Set up GitHub project board with Week 1 tasks as issues | Dev env running, repo initialized, examples reviewed |
| Tue — Day 2 | 8 hrs | WMS Domain Study | - Deep dive into Modula WMS import/export formats: Inventory, Orders, Picking, Serialization - Document each WMS entity: field name, data type, required/optional, accepted values - Identify the top 10 most commonly mapped customer fields (supervisor walk-through) - Begin drafting WMS Field Reference doc (Google Doc or Markdown — intern's choice) - Ask all domain questions — this is the designated Q&A day | WMS entity map drafted, top-10 field list confirmed with supervisor |
| Wed — Day 3 | 8 hrs | LLM & Agent Concepts | - Study LLM tool-use / function-calling pattern (Anthropic or OpenAI docs) - Set up API key, run a basic prompt → structured JSON response proof of concept - Research LangChain vs raw API for agent orchestration — write a 1-page decision note - Sketch the agent's high-level flow: input → parse → map → confirm → generate → validate - Review the Modula existing manual integration scripts to understand expected output format | LLM PoC working, decision note written |
| Thu — Day 4 | 8 hrs | Architecture Design | - Draw component diagram: FileIngestionModule, SchemaMapper, LLMClient, CodeGenerator, Validator - Define module interfaces (input/output types using Pydantic models) - Decide: monorepo layout, folder structure, config management approach - Document the confirmation/override flow — how does a human approve or correct a field mapping? - Write Architecture Decision Records (ADRs) for: LLM choice, orchestration approach, output format | Component diagram + ADRs drafted |
| Fri — Day 5 | 8 hrs | Architecture Review & Sign-Off | - Present architecture diagram and ADRs to supervisor — 30-minute review meeting - Incorporate feedback, finalize architecture doc - Define Week 2 sprint tasks on GitHub board (file parser module) - Finalize WMS Field Reference doc v0.1 — commit to repo - Write Week 1 status update (what was built, what was decided, blockers) | Architecture signed off — build may begin Week 2 |

## Week 1 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| Architecture Doc | Component diagram + module interfaces + ADRs committed to repo | Intern → Supervisor review |
| WMS Field Reference v0.1 | Entity map with field names, types, required flags, sample values — Markdown | Intern (living doc) |
| Dev Environment | Repo initialized, all deps installed, LLM API PoC script working | Intern self-verified |
| GitHub Project Board | Week 2 sprint tasks created as issues, assigned, estimated | Intern |
| Week 1 Status Update | Written summary: decisions made, questions answered, blockers | Intern → Supervisor |

⚠ Gate: Architecture Sign-Off Week 2 build work does not start until the architecture diagram and ADRs have been reviewed and approved by the supervisor. If sign-off is not achieved by Friday EOD, schedule a Monday morning 1:1 to resolve outstanding questions before coding begins.

# Week 2 — File Parsing Engine  (Hrs 41–80)

The intern builds the FileIngestionModule — the first production component. This module must reliably accept any CSV, XML, or JSON file a customer might send and return a normalized internal schema object that the rest of the agent can work with.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 6 | 8 hrs | CSV Parser | - Define the internal ParsedSchema Pydantic model: {filename, format, columns: [{name, sample_values, inferred_type}], row_count, encoding} - Build CSV parser: auto-detect delimiter (comma, tab, pipe, semicolon), encoding (UTF-8, Latin-1), and header row - Handle edge cases: quoted fields with commas, blank rows, BOM characters - Write unit tests: at least 5 CSV fixtures (standard, tab-delimited, quoted, no-header, UTF-16) | CSV parser passing all unit tests |
| Tue — Day 7 | 8 hrs | XML Parser | - Build XML parser using lxml: extract element names, attributes, text content, nesting depth - Flatten nested XML to column-like structure for schema comparison - Handle namespaces, CDATA sections, repeated elements (treat as array fields) - Write unit tests: flat XML, namespaced XML, deeply nested XML, repeated child elements - Add XPath-based sample value extractor (first 5 values per field) | XML parser passing all unit tests |
| Wed — Day 8 | 8 hrs | JSON Parser | - Build JSON parser: handle object, array-of-objects, and nested object structures - Flatten nested keys using dot notation (e.g., order.customer.id → order.customer.id) - Detect arrays of primitives vs arrays of objects — handle both - Infer field types: string, integer, float, boolean, date (ISO 8601 detection) - Write unit tests: flat JSON, nested JSON, array root, mixed types, null values | JSON parser passing all unit tests |
| Thu — Day 9 | 8 hrs | Format Detector & Integration | - Build auto-format detector: infer CSV/XML/JSON from extension + content sniffing (don't trust extension alone) - Unify all three parsers under a single ingest(filepath) → ParsedSchema interface - Add error handling: corrupted files, empty files, unsupported formats — return structured error, not stack trace - Integration test: single ingest() call correctly routes and parses all three formats - Log parsed schema summary to console (field count, row count, format detected) | Unified ingest() function working across all three formats |
| Fri — Day 10 | 8 hrs | Test Harness & Demo Prep | - Run parsers against all 3 provided real anonymized customer sample files - Fix any bugs found on real data (encoding issues, unexpected structure, etc.) - Write a quick CLI: python ingest.py --file sample.csv → prints ParsedSchema as formatted JSON - Demo to supervisor: live parsing of all three sample files via CLI - Write Week 2 status update; update GitHub board for Week 3 | File ingestion demo accepted by supervisor |

## Week 2 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| FileIngestionModule | ingest() function parsing CSV, XML, JSON → ParsedSchema; committed to repo | Intern → Supervisor demo |
| Unit Test Suite | 15+ tests across all formats and edge cases; all passing in CI | Intern self-verified |
| ParsedSchema Model | Pydantic model documented with field descriptions and example output | Intern |
| CLI Entry Point | python ingest.py --file <path> runs and prints schema summary | Intern |
| Week 2 Status Update | Written summary including real-data test results and any unexpected findings | Intern → Supervisor |

💡 Note on Real Data Running the parser against actual customer files almost always surfaces unexpected quirks — non-standard encodings, inconsistent column names across file versions, or files that use a .csv extension but are actually pipe-delimited. Document every quirk found; they become test fixtures and inform the LLM mapping prompts in Week 3.

# Week 3 — Schema Mapping with LLM Assistance  (Hrs 81–120)

The intern builds the SchemaMapper — the most intellectually interesting component. Given a ParsedSchema from Week 2 and the WMS Field Reference from Week 1, the LLM suggests which customer fields map to which Modula WMS fields. The human confirms or corrects the mapping before code generation proceeds.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 11 | 8 hrs | Mapping Data Model | - Define FieldMapping Pydantic model: {source_field, wms_field, confidence: float, match_reason: str, transform: str ¦ None, confirmed: bool} - Define MappingResult model: {mappings: list[FieldMapping], unmapped_source: list[str], unmapped_wms: list[str]} - Study the 3 example integrations from Week 1 — manually create expected MappingResult for each as golden test fixtures - Research prompt engineering patterns for structured JSON output from LLMs (system prompt design) | Data models defined, golden fixtures created for 3 examples |
| Tue — Day 12 | 8 hrs | LLM Prompt Engineering | - Write system prompt: gives LLM the WMS field dictionary, instructs it to return only JSON, defines confidence scoring rules - Write user prompt template: injects customer field names + sample values, asks for FieldMapping list - Iterate prompt in Anthropic/OpenAI playground until output is consistently valid JSON - Add few-shot examples to prompt using the golden fixtures from Day 11 - Test prompt against all 3 sample files — review mapping quality manually | Prompt producing valid, useful JSON mappings on all 3 samples |
| Wed — Day 13 | 8 hrs | LLMClient Module | - Build LLMClient class: wraps API call, handles retry on rate limit, parses JSON response, raises typed exceptions on failure - Add response validation: ensure returned JSON matches FieldMapping schema (Pydantic parse) - Implement confidence threshold: fields below 0.6 confidence are flagged as 'needs review' automatically - Cache LLM responses during development (avoid repeated API calls for same input — saves cost and time) - Unit test LLMClient with mocked API responses (no live API calls in test suite) | LLMClient working with mocked and live responses |
| Thu — Day 14 | 8 hrs | Confirmation Flow (CLI) | - Build interactive CLI confirmation step: display each suggested mapping, allow user to Accept / Reject / Override - For overrides: present list of valid WMS fields for user to select from (prevent typos) - For unmapped source fields: offer 'skip' or 'map to custom field' option - Save confirmed MappingResult to JSON file (audit trail — every confirmed mapping is logged with timestamp) - Test the full flow end-to-end: ingest → LLM map → CLI confirm → save MappingResult | Full ingest → map → confirm flow running interactively |
| Fri — Day 15 | 8 hrs | Accuracy Testing & Refinement | - Run full mapping flow against all 3 sample files; measure: how many LLM suggestions were accepted vs overridden - For any incorrect suggestions: adjust prompt with additional context or examples - Document mapping accuracy results in a simple table (source file, total fields, auto-accepted, overridden, missed) - Demo to supervisor: full ingest → map → confirm flow on live sample - Write Week 3 status update; update GitHub board for Week 4 | Mapping accuracy documented; demo accepted by supervisor |

## Week 3 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| SchemaMapper Module | LLM-assisted field mapping with confidence scoring; committed to repo | Intern → Supervisor demo |
| LLMClient Class | API wrapper with retry, response validation, mock support; unit tested | Intern |
| CLI Confirmation Flow | Interactive mapping review: accept/reject/override with WMS field picker | Intern |
| Mapping Audit Log | JSON output of every confirmed mapping with timestamp — append-only log file | Intern |
| Accuracy Report | Table showing auto-accept vs override rate per sample file | Intern → Supervisor |
| Week 3 Status Update | Written summary with accuracy numbers and prompt iteration notes | Intern → Supervisor |

💡 Prompt Tip Include 3–5 real mapping examples directly in the system prompt (few-shot). For example: 'ITEM_NO → wms_part_number (confidence: 0.95), SERIAL → wms_serial_id (confidence: 0.88)'. This single change typically improves first-pass accuracy by 20–30% over zero-shot prompting.

# Week 4 — Code Generation & End-to-End Integration  (Hrs 121–160)

The intern builds the CodeGenerator — taking a confirmed MappingResult and producing an executable transformation script. By Friday, the full Phase 1 pipeline runs end-to-end: file in → schema parsed → fields mapped → script generated → script validated against WMS import format.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 16 | 8 hrs | Code Generator Design | - Decide output script language with supervisor: Python recommended (aligns with rest of project) - Study Modula WMS import file format requirements in detail — what does a valid import look like? - Design template system: Jinja2 templates for transformation script skeleton - Define templates for: CSV→WMS, XML→WMS, JSON→WMS (three separate templates) - Build CodeGenerator class: takes MappingResult + source format + output path → renders template | Template system designed, CodeGenerator class skeleton committed |
| Tue — Day 17 | 8 hrs | Template Implementation | - Implement CSV→WMS template: read source CSV, apply column renames, apply transforms (date format, strip whitespace, type cast), write WMS-formatted output - Implement XML→WMS template: parse XML with XPath expressions derived from mapping, flatten to WMS row structure - Implement JSON→WMS template: traverse dot-notation paths from mapping, extract values, write WMS output - Add transform helpers to template context: date_format(), pad_left(), strip(), to_int(), default_if_null() - Generate test scripts from the 3 golden MappingResult fixtures — review output manually | All three templates generating syntactically correct Python scripts |
| Wed — Day 18 | 8 hrs | Output Validation | - Build Validator class: runs the generated script against a small sample (first 10 rows), checks output matches WMS import schema - Validation checks: required WMS fields present, data types correct, no null values in required columns, row count matches input - If validation fails: return structured ValidationResult with list of errors (field name, row number, error type) - Add validation step to pipeline: CodeGenerator output → Validator → pass/fail report - Test validation against intentionally broken mappings to confirm errors are caught | Validator catching schema errors reliably on test cases |
| Thu — Day 19 | 8 hrs | Full Pipeline Integration | - Wire all modules together: ingest() → LLMClient.map() → CLI confirm → CodeGenerator.generate() → Validator.validate() - Build a single pipeline runner script: python run_pipeline.py --file customer.csv --output ./output/ - Run full pipeline against all 3 real sample files — fix any integration bugs - Ensure output folder structure is clean: /output/{timestamp}/{source_file}/mapping.json + transform_script.py + validation_report.txt - Add basic logging throughout the pipeline (INFO level to console, DEBUG to log file) | Full pipeline running cleanly on all 3 sample files |
| Fri — Day 20 | 8 hrs | Code Review & Phase 1 Demo | - Prepare demo: walk supervisor through full pipeline on a real sample file — live, not pre-recorded - Code review with supervisor: architecture adherence, code quality, test coverage, docstrings - Document all known limitations and edge cases in a LIMITATIONS.md file in the repo - Write Phase 1 retrospective: what went well, what was harder than expected, what would be done differently - Set up Week 5 sprint on GitHub board (REST API foundations); write Week 4 status update | Phase 1 demo accepted; code review complete; Phase 2 sprint ready |

## Week 4 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| CodeGenerator Module | Jinja2-based script generator for CSV/XML/JSON → WMS; committed to repo | Intern → Supervisor review |
| Validator Module | Schema + type validation on generated script output; returns structured errors | Intern |
| Pipeline Runner | python run_pipeline.py --file --output runs full end-to-end flow | Intern → Supervisor demo |
| Output Package | Per-run output folder: mapping JSON + transform script + validation report | Intern |
| LIMITATIONS.md | Honest list of known edge cases, unsupported scenarios, and future improvements | Intern |
| Phase 1 Retrospective | Written retrospective — pasted into project wiki or README | Intern → Supervisor |
| Week 4 Status Update | Final Phase 1 summary; confirmation that Phase 2 sprint is ready | Intern → Supervisor |

✅ Phase 1 Exit Criteria Before proceeding to Week 5 (REST API), all of the following must be true: • Full pipeline runs without errors on all 3 real sample files • Validator catches at least 3 distinct error types in test cases • Code review completed with no critical issues open • All Week 1–4 deliverables committed to repo • Supervisor has signed off on Phase 1 demo

# Appendix — Reference Material for Intern

## Recommended Reading (Week 1)

- Anthropic Claude Tool Use docs — function calling pattern

- Pydantic v2 docs — model definition, validation, serialization

- Python csv module docs + chardet library for encoding detection

- lxml etree tutorial — XPath and element traversal

- Jinja2 template documentation — filters, macros, environment setup

- GitHub Flow guide — branching, PRs, commit message conventions

## Suggested Repo Structure

| Path | Purpose |
| --- | --- |
| agent/ingestion/ | FileIngestionModule — parsers for CSV, XML, JSON |
| agent/mapping/ | SchemaMapper, LLMClient, FieldMapping models |
| agent/generation/ | CodeGenerator, Jinja2 templates |
| agent/validation/ | Validator, ValidationResult model |
| agent/cli/ | CLI entry points (ingest.py, run_pipeline.py) |
| tests/ | Unit and integration tests, fixture files |
| tests/fixtures/ | Sample customer files, golden MappingResult JSONs |
| output/ | Generated files (git-ignored) |
| docs/ | WMS Field Reference, Architecture doc, ADRs |
| docs/adrs/ | Architecture Decision Records (one .md per decision) |

## Weekly Rhythm

- Monday AM — Sprint planning: review GitHub board, confirm day-by-day priorities

- Wednesday — Mid-week check-in (async Slack message or 15-min standup): progress vs plan

- Friday PM — 1:1 with supervisor: demo or walkthrough, status update submitted, next week's board updated

- Friday EOD — Git push: everything committed; no work-in-progress code sitting only on local machine

## Escalation Rule

The 48-Hour Rule If the intern is blocked on a technical problem for more than 48 hours without progress, they must flag it to the supervisor immediately — do not lose a full sprint day trying to solve something in isolation. Blockers are not failures; undisclosed blockers are.

Document prepared by: Software Implementation Team  |  Modula USA  |  May 2026