MODULA USA

WMS / ERP Integration AI Agent

Internship Project Outline  |  13-Week Program  |  Software Implementation Team

# 1. Project Overview

Modula USA's Software Implementation team regularly onboards customers whose ERP and WMS systems require custom data exchange — moving inventory transactions, order data, and serialization records between Modula WMS and platforms such as SAP, Oracle, NetSuite, Epicor, Dynamics, and others. Today this middleware is built manually for each engagement.

The goal of this internship project is to design and build an Agentic AI system that accelerates this process. Given sample data files or API documentation from a customer, the agent will analyze the data schema, map fields to Modula WMS structures, and generate functional middleware code — targeting file-based exchange (CSV/XML/JSON), REST API integration, and ODBC/SQL direct connections.

## Core Objectives

- Reduce time-to-integration from days to hours per customer engagement

- Produce reusable, maintainable middleware templates the team can extend

- Build an agent that understands Modula WMS data structures natively

- Support all three primary integration patterns used in the field

# 2. Scope of Work

## Integration Methods Targeted

| Phase | Focus | Deliverables | Duration |
| --- | --- | --- | --- |

| File-Based | CSV, XML, JSON parsing & generation | Inbound/outbound file watchers, schema mapping, transformation scripts | Weeks 1–4 |
| --- | --- | --- | --- |
| REST API | HTTP client, OAuth 2.0 auth (industry standard); legacy fallbacks for older ERPs | API connector framework, endpoint discovery, JSON↔WMS mapping | Weeks 5–8 |
| ODBC / SQL | Direct DB connections, query generation | SQL query builder, schema introspection, bidirectional sync logic | Weeks 9–11 |
| Agent Wrapper | Orchestration, UI, and packaging | Chat interface, input processor, output validator, documentation | Weeks 12–13 |

## Out of Scope

- Production deployment to live customer environments

- Building or modifying core Modula WMS application code

- Real-time streaming or event-driven architectures (future phase)

# 3. 13-Week Schedule

| Week(s) | Theme | Tasks | Outcome |
| --- | --- | --- | --- |
| 1 | Onboarding & Architecture | Environment setup, review Modula WMS data dictionary, study 3 real integration examples, define agent architecture (LLM + tool use) | Architecture diagram, Modula schema reference doc |
| 2 | File Parsing Engine | Build CSV/XML/JSON parsers, auto-detect delimiters and encoding, extract column headers and sample rows | File ingestion module with test suite |
| 3 | Schema Mapping — File | Design field-mapping logic, build LLM prompt to suggest WMS field matches, allow override/confirmation step | Schema mapper v1 with file input |
| 4 | Code Generation — File | Generate Python/PowerShell transformation scripts from confirmed map, validate output against WMS import format | End-to-end file integration generator |
| 5 | REST API Foundations | HTTP client library with OAuth 2.0 as default auth standard; API Key and Basic Auth as legacy fallbacks; parse OpenAPI/Swagger specs if available | API auth + spec parser module |
| 6 | REST Endpoint Discovery | Agent prompts user for base URL + sample call, infers available endpoints, maps responses to WMS fields | REST connector framework |
| 7 | Code Generation — REST | Generate API polling/push scripts, error handling, retry logic, logging | REST integration generator + sample output |
| 8 | REST Testing & Refinement | Test against mock ERP APIs (mock SAP, NetSuite), fix edge cases, add response validation | Tested REST generator with 2+ ERP mocks |
| 9 | ODBC/SQL Foundations | pyodbc / SQLAlchemy setup, SQL Server + common ERP DB connection profiles, schema introspection queries | DB connection module + schema reader |
| 10 | SQL Query Builder | LLM-assisted SELECT/INSERT/UPDATE generation from WMS field mappings, parameterized queries, no raw string injection | SQL query generator with safety review |
| 11 | Bidirectional Sync Logic | Change detection (timestamp/delta), conflict handling rules, transaction logging, rollback sketch | Sync engine draft with logging |
| 12 | Agent Orchestration | Unify all three modules under a single agent interface, build input wizard (upload file OR paste API info OR enter DB conn string) | Unified agent CLI or web UI |
| 13 | Demo, Docs & Handoff | End-to-end demo with real anonymized customer data, write developer handoff guide, present findings and roadmap | Demo recording, handoff doc, roadmap slide |

# 4. Technical Stack & Tools

The intern should have latitude to propose alternatives, but the following stack aligns with existing Modula USA tooling and SQL Server infrastructure:

| Technical Skills | Tools / Platforms | Professional Skills |
| --- | --- | --- |
| Python 3.11+ | VS Code / Cursor | Weekly 1:1 with supervisor |
| LLM API (Claude/OpenAI) | GitHub (version control) | Written status updates (Friday) |
| pyodbc / SQLAlchemy | Postman (API testing) | Sprint planning (2-week cycles) |
| FastAPI or Flask (UI layer) | SQL Server 2019/2022 (dev) | Peer code review |
| Pydantic (data validation) | Docker (optional isolation) | Documentation standards |
| OpenAPI / Swagger parsing | Modula WMS (test instance) | Final presentation (Week 13) |

# 5. Deliverables Summary

## Code Artifacts

- File integration generator — accepts CSV/XML/JSON, outputs transformation script

- REST integration generator — accepts API info, outputs polling/push script

- SQL/ODBC integration generator — accepts connection info, outputs sync script

- Unified agent interface — single entry point wrapping all three generators

## Documentation

- Modula WMS field reference guide (intern-authored, reusable by team)

- Developer handoff doc — setup, architecture, extension guide

- User guide — how an implementation engineer uses the agent in the field

## Demonstration

- Live or recorded demo using anonymized real customer data from at least two integration types

- Slide deck summarizing architecture decisions, challenges, and recommended next steps

# 6. Success Criteria

At the end of 13 weeks, the project will be considered successful if the following conditions are met:

- The agent correctly maps fields from at least 3 different sample files to Modula WMS fields with >80% accuracy before human review

- Generated middleware scripts execute without modification (or with only minor tweaks) against test data

- The tool covers all three integration types — file, REST, and ODBC/SQL

- A Modula implementation engineer with no knowledge of the project can operate the tool using only the user guide

- Code is version-controlled, documented, and transferable to the team

# 7. Supervision & Support

- Weekly 1:1 check-ins with the Software Supervisor to review progress, unblock issues, and adjust scope

- Access to a Modula WMS test instance and sanitized sample customer integration files for development

- Intern is expected to flag blockers within 48 hours rather than losing sprint time

- Code reviews at the end of each phase (Weeks 4, 8, 11, 13)

## Suggested Checkpoints

- Week 2 — Architecture sign-off before build begins

- Week 4 — File integration demo to supervisor

- Week 8 — REST integration demo; scope adjustment if needed

- Week 11 — SQL sync engine review

- Week 13 — Final presentation to Software team

# 8. Future Roadmap (Beyond Internship)

This section captures ideas that are intentionally out of scope for 13 weeks but should inform the agent's architecture so they remain feasible extensions:

- Salesforce Work Order integration — push/pull WMS events to Salesforce CRM (aligns with existing Modula Salesforce template work)

- Support for additional ERP platforms — expand beyond initial mocks to include Epicor, Infor, and Sage

- Web-based UI — replace CLI wizard with a browser interface accessible to non-developer implementation staff

- Auto-testing framework — agent generates not just the middleware but also a test harness to validate it

- Customer self-service portal — long-term vision where customers upload their own files and receive integration packages directly

Document prepared by: Software Implementation Team  |  Modula USA  |  May 2026