MODULA USA

WMS / ERP Integration AI Agent — Phase 2 Detail Schedule

Weeks 5–8  |  REST API Integration  |  Full-Time (40 hrs/week)

Phase 2 Goal By end of Week 8, the intern will have built a working REST API integration generator: given a customer's API base URL, auth credentials, and either an OpenAPI spec or sample request/response payloads, the agent will discover available endpoints, map response fields to Modula WMS structures, and generate tested polling and push scripts — extending the same pipeline architecture from Phase 1.

Phase 1 Prerequisite Phase 2 begins only after the Phase 1 exit criteria have been met: file pipeline running cleanly on all sample files, code review passed, and supervisor sign-off received on the Phase 1 demo. The REST module is built as an additional connector within the same agent architecture — do not rebuild shared components.

# Week 5 — REST API Foundations  (Hrs 161–200)

The intern builds the core REST infrastructure that all subsequent API work depends on: an HTTP client with robust auth support, an OpenAPI/Swagger spec parser, and a framework for normalizing API responses into the same ParsedSchema model used in Phase 1. This week is deliberately foundational — no code generation yet.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 21 | 8 hrs | HTTP Client & Auth Patterns | - Review the 3 real customer integrations from Week 1 — identify which used REST APIs and what auth methods were present - Build APIClient class using the requests library: configurable base URL, default headers, timeout, session reuse - Implement auth strategy pattern: OAuth 2.0 Client Credentials is the primary standard and default — also support API Key (header or query param) and Basic Auth as legacy fallbacks for older ERP systems - Write unit tests for each auth method using responses library (mock HTTP — no live calls in test suite) - Test APIClient against a public REST API (e.g., JSONPlaceholder) to confirm live behavior | APIClient with OAuth 2.0 as default + legacy fallbacks passing unit tests |
| Tue — Day 22 | 8 hrs | OpenAPI / Swagger Spec Parsing | - Study OpenAPI 3.0 and Swagger 2.0 spec structure — understand paths, operations, schemas, components - Build SpecParser class: loads spec from URL (e.g., /openapi.json) or local file, extracts endpoint list with method, path, parameters, and response schema - Map response schema fields to an EndpointSchema Pydantic model: {path, method, response_fields: [{name, type, nullable, description}]} - Handle specs that use $ref references — resolve them to their actual schema definitions - Write tests using 2–3 real open-source OpenAPI specs (e.g., Petstore, GitHub public API subset) | SpecParser extracting endpoint + field lists from real specs |
| Wed — Day 23 | 8 hrs | No-Spec Fallback: Sample Payload Analysis | - Many customer APIs have no spec — build SampleAnalyzer: accepts a raw JSON response payload, infers field names, types, nesting depth, array vs object - Flatten nested JSON to dot-notation field list (reuse logic from Phase 1 JSON parser where possible) - Prompt intern to make this a shared utility — refactor Phase 1 JSON flattener into a common module if it isn't already - SampleAnalyzer output: same EndpointSchema model as SpecParser — both paths merge at the same interface - Test: feed 5 different real-world-style API response shapes, verify consistent field extraction | SampleAnalyzer producing EndpointSchema matching SpecParser output format |
| Thu — Day 24 | 8 hrs | Response Normalization & ParsedSchema Bridge | - Build ResponseNormalizer: takes EndpointSchema and maps it to the ParsedSchema model from Phase 1 — so the existing SchemaMapper and CodeGenerator can be reused without modification - This is the key architectural insight of Phase 2: the LLM mapping and code generation modules are format-agnostic once input is normalized - Write integration test: SpecParser → ResponseNormalizer → ParsedSchema → confirm fields match expected WMS mappings - Document the normalization contract in the architecture doc (update Week 1 component diagram) - Review with supervisor: confirm the normalization approach before building on it further | ResponseNormalizer bridge working; architecture doc updated |
| Fri — Day 25 | 8 hrs | Auth Testing & Week 5 Review | - Set up mock ERP API server locally using FastAPI or WireMock — this becomes the test harness for Weeks 6–8 - Mock server should simulate: an inventory endpoint (GET), an order push endpoint (POST), and a token endpoint (OAuth 2.0) - Run APIClient + SpecParser against the mock server end-to-end — confirm full auth → spec parse → normalize flow - Write Week 5 status update; update GitHub board for Week 6 - Supervisor review: confirm mock server design is sufficient for testing purposes | Mock ERP server running; full foundation stack tested against it |

## Week 5 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| APIClient Class | HTTP client with OAuth 2.0 as default; API Key and Basic Auth as legacy fallbacks; unit tested | Intern → Supervisor |
| SpecParser Class | OpenAPI/Swagger parser → EndpointSchema; tested against 2+ real specs | Intern |
| SampleAnalyzer Class | JSON payload analyzer → EndpointSchema; same output format as SpecParser | Intern |
| ResponseNormalizer | EndpointSchema → ParsedSchema bridge; integration tested | Intern → Supervisor review |
| Mock ERP API Server | FastAPI mock with GET inventory, POST order, OAuth token endpoints | Intern (used Weeks 6–8) |
| Week 5 Status Update | Written summary; architecture doc updated with normalization contract | Intern → Supervisor |

💡 Reuse Principle The Phase 2 architecture wins if the intern never has to modify SchemaMapper or the LLM prompt — they should work identically whether the input came from a CSV file or a REST API response. If changes to those modules are needed, escalate to the supervisor before making them; it likely means the normalization layer needs adjusting instead.

# Week 6 — REST Endpoint Discovery & Mapping  (Hrs 201–240)

The intern builds the interactive endpoint discovery flow — the equivalent of Week 3's confirmation CLI but for REST APIs. The agent walks the user through identifying which endpoints to poll or push, confirms field mappings, and handles the added complexity of pagination, rate limits, and nested response structures.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 26 | 8 hrs | Endpoint Discovery CLI | - Build EndpointDiscovery module: presents user with list of discovered endpoints from SpecParser or SampleAnalyzer, asks them to select which to integrate (GET for pull, POST/PUT for push) - For each selected endpoint: display field list with inferred types and sample values - Add endpoint metadata capture: polling frequency (on-demand / scheduled / event-triggered), direction (inbound to WMS / outbound from WMS) - Store selections as EndpointConfig Pydantic model: {url, method, auth_strategy, direction, polling_frequency, selected_fields} - Test the discovery flow against the mock ERP server from Week 5 | EndpointDiscovery CLI selecting and storing endpoint configs |
| Tue — Day 27 | 8 hrs | LLM Mapping for REST Fields | - Route EndpointConfig through existing SchemaMapper — confirm Phase 1 LLM prompt handles REST field names as well as file column names - If accuracy drops vs. file-based input: add REST-specific context to system prompt (e.g., 'Fields come from a REST API response; names may use camelCase or snake_case') - Run mapping accuracy test: compare auto-accept rate for REST fields vs. file fields — document in accuracy report - Add handling for nested field paths in mapping: e.g., order.customer.id should map to wms_customer_id with a flattening transform noted - Update CLI confirmation flow to show full dot-notation path alongside the suggested WMS field | LLM mapping working for REST fields with accuracy documented |
| Wed — Day 28 | 8 hrs | Pagination & Rate Limit Handling | - Build PaginationHandler: detects common pagination patterns — page/per_page query params, offset/limit, cursor-based (next_cursor in response), Link header (RFC 5988) - PaginationHandler iterates pages and yields normalized records as a stream — CodeGenerator will wrap this in generated scripts - Build RateLimitHandler: reads Retry-After header on 429 responses, implements exponential backoff with jitter, configurable max retries - Add rate limit config to EndpointConfig: requests_per_minute field with default of 60 - Test both handlers against mock server endpoints configured to paginate and return 429s | Pagination and rate limit handlers tested against mock server |
| Thu — Day 29 | 8 hrs | Push Endpoint Support | - Extend EndpointConfig for push (POST/PUT) endpoints: add request_body_schema field — what does the API expect as input? - Build RequestBodyBuilder: takes WMS export data + field mapping + target endpoint schema and constructs a properly formatted JSON request body - Handle common push patterns: single-record POST, batch array POST, PATCH for partial updates - Add response validation for push endpoints: check HTTP 200/201/204, parse error bodies, log failures with full request context - Test RequestBodyBuilder: send constructed payloads to mock POST endpoint, verify acceptance | Push endpoint support working end-to-end against mock server |
| Fri — Day 30 | 8 hrs | Full Discovery Flow Demo & Review | - Run complete discovery flow on mock server: auth → spec parse → endpoint select → field map → confirm → EndpointConfig saved - Run same flow using SampleAnalyzer path (no spec — paste raw JSON response) — confirm both paths produce equivalent EndpointConfig - Demo to supervisor: full Week 5–6 stack working on mock ERP - Write Week 6 status update; update accuracy report with REST mapping numbers - Update GitHub board for Week 7 | Full discovery demo accepted by supervisor; both spec and no-spec paths working |

## Week 6 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| EndpointDiscovery Module | CLI for selecting endpoints, direction, frequency; stores EndpointConfig | Intern → Supervisor demo |
| PaginationHandler | Detects and iterates page/offset/cursor/Link-header pagination patterns | Intern; tested on mock |
| RateLimitHandler | Exponential backoff on 429; Retry-After header support; configurable limit | Intern; tested on mock |
| RequestBodyBuilder | Constructs POST/PUT request bodies from WMS data + mapping + target schema | Intern |
| Updated Accuracy Report | REST field mapping auto-accept rate vs. file-based; any prompt changes noted | Intern → Supervisor |
| Week 6 Status Update | Written summary; both discovery paths (spec + no-spec) confirmed working | Intern → Supervisor |

# Week 7 — REST Code Generation  (Hrs 241–280)

The intern extends the CodeGenerator from Phase 1 with REST-specific Jinja2 templates. The generated scripts must be production-quality: they handle auth token refresh, pagination, rate limiting, structured logging, and error recovery — not just a happy-path HTTP call.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 31 | 8 hrs | REST Polling Template | - Design the REST pull (polling) script template structure: auth setup → paginate → extract fields → transform → write to WMS import format - Implement Jinja2 template: rest_pull.py.j2 — parameterized by EndpointConfig + FieldMapping - Generated script must include: token refresh logic (if OAuth), PaginationHandler call, field extraction using dot-notation paths from mapping, output to WMS CSV/JSON format - Generate a test script from mock ERP inventory endpoint config — run it, confirm output matches WMS format - Add CLI flag to pipeline runner: --integration-type rest | REST pull template generating executable, correct polling script |
| Tue — Day 32 | 8 hrs | REST Push Template | - Implement Jinja2 template: rest_push.py.j2 — reads WMS export data, constructs request body via RequestBodyBuilder logic, POSTs to endpoint - Generated script must include: batch size control (configurable, default 100 records/call), retry on transient errors (5xx, timeout), success/failure logging per record - Generate a test push script from mock ERP order endpoint — run against mock server, verify payloads accepted - Handle both single-record and batch-array push patterns in the template (toggle via EndpointConfig) - Add idempotency key header injection where the API supports it (configurable) | REST push template generating executable push script; batch and single-record modes working |
| Wed — Day 33 | 8 hrs | Error Handling & Logging Framework | - All generated scripts must use Python logging module — not print(). Add structured log formatter: JSON lines format for easy parsing - Define standard log events: POLL_START, POLL_PAGE, RECORD_PROCESSED, RECORD_FAILED, PUSH_SENT, PUSH_FAILED, TOKEN_REFRESHED, RATE_LIMITED - Add dead-letter queue pattern: failed records written to a failed_records_{timestamp}.json file for manual review — not silently dropped - Add a --dry-run flag to generated scripts: runs full flow but does not write to WMS or push to API — useful for testing mapping accuracy on live data - Test dry-run mode against live JSONPlaceholder API — confirm no side effects | Structured logging and dead-letter file in all generated scripts; dry-run flag working |
| Thu — Day 34 | 8 hrs | Scheduler Scaffold & Config File | - Generated scripts should be runnable stand-alone OR via a scheduler — add a config YAML file alongside each generated script: endpoint URL, auth, polling interval, field mapping path - Build a simple scheduler scaffold: schedule library wraps the generated script function, runs it at configured interval, logs next-run time - This is not a full scheduler — it is a scaffold the customer's IT team can drop into their existing task scheduler (Windows Task Scheduler, cron, etc.) - Add a --once flag: run the poll/push exactly once and exit — useful for manual trigger and testing - Document the scheduler scaffold pattern in the developer handoff doc | Config YAML + scheduler scaffold generated alongside every script |
| Fri — Day 35 | 8 hrs | Full REST Pipeline Test | - Run full REST pipeline on mock ERP server: auth → discover → map → confirm → generate pull script → generate push script → run both - Measure: total time from 'user provides base URL' to 'working scripts in output folder' — this is a key usability metric - Run pipeline a second time using SampleAnalyzer path (no spec) — confirm equivalent output - Write Week 7 status update; record time-to-integration metric - Update GitHub board for Week 8 | Full REST pipeline producing working pull + push scripts; time-to-integration measured |

## Week 7 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| rest_pull.py.j2 Template | Jinja2 polling template with pagination, token refresh, WMS output | Intern; tested on mock |
| rest_push.py.j2 Template | Jinja2 push template with batch control, retry, idempotency key support | Intern; tested on mock |
| Logging Framework | Structured JSON-lines logging + dead-letter file in all generated scripts | Intern |
| Scheduler Scaffold | Config YAML + schedule wrapper generated with every script | Intern |
| Time-to-Integration Metric | Measured minutes from 'base URL provided' to 'working scripts'; recorded in status | Intern → Supervisor |
| Week 7 Status Update | Written summary with pipeline run results on mock server (both paths) | Intern → Supervisor |

# Week 8 — REST Testing, ERP Mocks & Phase 2 Close  (Hrs 281–320)

The intern hardens the REST integration generator against real-world ERP API patterns, expands the mock ERP library, fixes edge cases discovered on live APIs, and closes Phase 2 with a supervisor demo and code review before Phase 3 begins.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 36 | 8 hrs | SAP Business One Mock | - Research SAP Business One Service Layer REST API structure — endpoint patterns, OData query syntax, session auth (cookie-based — note this is a legacy SAP pattern, not OAuth 2.0) - Extend mock ERP server with SAP B1-style endpoints: /Items (inventory), /Orders (order push), /Login (session cookie auth) - Run full pipeline against SAP B1 mock — identify any failures with OData $filter/$select query params or cookie auth - Fix APIClient to support cookie-based session auth as a legacy exception for SAP B1 — document clearly that OAuth 2.0 is preferred and this is an ERP-specific workaround - Document SAP B1 integration pattern in a 1-page integration profile (template for future ERP profiles) | SAP B1 mock passing full pipeline; cookie auth added to APIClient |
| Tue — Day 37 | 8 hrs | NetSuite REST Mock | - Research NetSuite REST Record API — Record endpoint structure, SuiteQL for complex queries; note NetSuite uses TBA OAuth 1.0 signature auth (a legacy exception — most modern ERPs use OAuth 2.0) - Extend mock server with NetSuite-style endpoints: /record/v1/inventoryItem, /record/v1/salesOrder, OAuth 1.0 token endpoint - OAuth 1.0 is a legacy standard — implement OAuth 1.0 signature generation in APIClient as a named legacy exception, clearly separated from the OAuth 2.0 default path - Run full pipeline against NetSuite mock — confirm OAuth 1.0 signing works correctly - Document NetSuite integration profile (same template as SAP B1) | NetSuite mock passing full pipeline; OAuth 1.0 strategy added |
| Wed — Day 38 | 8 hrs | Edge Case Hardening | - Test pipeline against APIs that return inconsistent field presence (sometimes a field is present, sometimes missing) - Test pipeline with APIs that return HTML error pages instead of JSON on 4xx/5xx — ensure parser doesn't crash - Test pipeline with very large paginated responses (simulate 10,000+ records across 100 pages) — confirm memory usage is acceptable (streaming, not loading all pages into memory) - Test token expiry mid-run — confirm refresh logic triggers correctly and run resumes without data loss - Add all discovered edge cases as test fixtures in the test suite | All edge cases handled and covered by tests |
| Thu — Day 39 | 8 hrs | Code Review & Documentation | - Full Phase 2 code review with supervisor: APIClient, SpecParser, SampleAnalyzer, ResponseNormalizer, EndpointDiscovery, PaginationHandler, RateLimitHandler, RequestBodyBuilder, both Jinja2 templates - Address all critical code review findings before end of day - Update LIMITATIONS.md: document all known unsupported API patterns (SOAP/WSDL, GraphQL, SFTP-based 'APIs', binary response formats) - Update developer handoff doc with Phase 2 architecture, new modules, and ERP integration profiles - Ensure all new modules have docstrings and are covered in README | Code review complete; all critical issues resolved; docs updated |
| Fri — Day 40 | 8 hrs | Phase 2 Demo & Sprint Planning | - Phase 2 demo to supervisor: full pipeline on SAP B1 mock (spec path) and NetSuite mock (no-spec / sample payload path) - Show both pull and push generated scripts running, logs output, dry-run mode, dead-letter file - Confirm Phase 2 exit criteria (see below) are all met - Write Phase 2 retrospective: what was harder than expected (auth complexity, pagination variety), what was easier, what would be done differently - Plan Phase 3 sprint on GitHub board (ODBC/SQL — Week 9 tasks as issues); write Week 8 status update | Phase 2 demo accepted; retrospective written; Phase 3 board ready |

## Week 8 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| SAP B1 Integration Profile | 1-page doc: auth method, key endpoints, OData quirks, pipeline test results | Intern |
| NetSuite Integration Profile | 1-page doc: OAuth 1.0 legacy exception, Record API endpoints, pipeline test results | Intern |
| OAuth 1.0 Legacy Support | APIClient OAuth 1.0 signature generation as named legacy exception; clearly documented | Intern |
| Edge Case Test Suite | Tests for missing fields, HTML errors, large paginated data, mid-run token expiry | Intern |
| Phase 2 Code Review | Completed review with supervisor; all critical findings resolved | Intern + Supervisor |
| Phase 2 Retrospective | Written retrospective committed to project wiki | Intern → Supervisor |
| Week 8 Status Update | Final Phase 2 summary; Phase 3 board confirmed ready | Intern → Supervisor |

✅ Phase 2 Exit Criteria Before proceeding to Week 9 (ODBC/SQL), all of the following must be true: • Full REST pipeline (spec and no-spec paths) producing working pull and push scripts • Pipeline tested against at least 2 ERP mock profiles (SAP B1, NetSuite) • OAuth 2.0 is the default auth method; OAuth 1.0 (NetSuite) and cookie auth (SAP B1) implemented as documented legacy exceptions • Code review completed with no critical issues open • Phase 1 modules (SchemaMapper, LLMClient, CodeGenerator base) unchanged • Supervisor has signed off on Phase 2 demo

Document prepared by: Software Implementation Team  |  Modula USA  |  May 2026