MODULA USA

WMS / ERP Integration AI Agent — Phase 3 Detail Schedule

Weeks 9–13  |  ODBC/SQL Integration + Agent Orchestration + Final Demo  |  Full-Time (40 hrs/week)

Phase 3 Goal Weeks 9–11 add the third and final integration method: direct ODBC/SQL database connections for customers whose ERP exposes data through a shared database rather than files or APIs. Weeks 12–13 unify all three modules under a single agent interface and close the internship with a complete end-to-end demo, developer handoff documentation, and a roadmap presentation to the Software Implementation team.

Phase 2 Prerequisite Phase 3 begins only after the Phase 2 exit criteria have been met: REST pipeline working on SAP B1 and NetSuite mocks, code review passed, and supervisor sign-off received. The ODBC module follows the same normalization contract established in Phase 2 — input is normalized to ParsedSchema before mapping and code generation.

# Week 9 — ODBC / SQL Foundations  (Hrs 321–360)

The intern builds the database connection layer: pyodbc/SQLAlchemy setup, schema introspection queries, and the bridge from SQL result sets to the shared ParsedSchema model. SQL Server is the primary target (aligning with Modula WMS infrastructure), with a secondary focus on common ERP database platforms.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 41 | 8 hrs | DB Connection Module | - Install and verify: pyodbc, SQLAlchemy, SQL Server ODBC driver (msodbcsql17 or 18) - Build DBConnector class: accepts connection string or named DSN, wraps pyodbc connection with context manager, exposes execute(sql, params) and fetch_schema(table) methods - Implement connection profiles for target databases: SQL Server, MySQL, PostgreSQL, Oracle (via cx_Oracle optional) - Use parameterized queries throughout — never string-interpolate user input into SQL - Write unit tests using SQLite as an in-process database (no SQL Server install needed for CI) | DBConnector class working against SQLite test DB; SQL Server profile defined |
| Tue — Day 42 | 8 hrs | Schema Introspection | - Build SchemaInspector class: connects to a database and returns a list of tables, views, and stored procedures available to the provided credentials - For each table/view: fetch column names, data types, nullable flags, primary keys, and foreign key relationships using INFORMATION_SCHEMA queries (works across SQL Server, MySQL, PostgreSQL) - Map SQL data types to the same type vocabulary used in ParsedSchema: string, integer, float, boolean, datetime - Generate sample values: execute SELECT TOP 5 * FROM {table} to populate sample_values in the schema - Write tests using SQLite with fixture tables matching common ERP table patterns (items, orders, customers) | SchemaInspector returning full table/column metadata with sample values |
| Wed — Day 43 | 8 hrs | ParsedSchema Bridge for SQL | - Build SQLNormalizer: takes SchemaInspector output for a selected table/view and produces a ParsedSchema — identical output to Phase 1 file parsers and Phase 2 ResponseNormalizer - This completes the three-path normalization architecture: File → ParsedSchema, REST → ParsedSchema, SQL → ParsedSchema - Write integration test: SQLNormalizer output → SchemaMapper → confirm LLM mapping works without changes to SchemaMapper - Add SQL-specific context hint to LLM system prompt (optional): 'Fields come from a SQL database table; names may use PascalCase, snake_case, or ALL_CAPS conventions' - Update architecture diagram to show all three normalization paths converging | SQLNormalizer producing ParsedSchema; SchemaMapper working unchanged |
| Thu — Day 44 | 8 hrs | Table & View Discovery CLI | - Build SQLDiscovery module: interactive CLI that presents all tables/views to user, allows selection of source table(s) for pull or target table for push - Display table metadata: row count estimate (from sys.dm_db_partition_stats on SQL Server, or COUNT(*) fallback), column count, sample row - Allow joining across tables: user can specify a simple JOIN condition — SQLDiscovery records it in SQLSourceConfig Pydantic model - SQLSourceConfig model: {connection_string, source_table, join_clause (optional), filter_clause (optional), selected_columns, direction} - Test discovery against SQLite fixture DB with 3 tables: items, item_locations, orders | SQLDiscovery CLI selecting tables, recording SQLSourceConfig |
| Fri — Day 45 | 8 hrs | SQL Server Live Test & Week 9 Review | - Connect DBConnector to the Modula WMS SQL Server test instance (supervisor provides read-only credentials) - Run SchemaInspector against actual Modula WMS tables — compare discovered schema to the WMS Field Reference doc from Week 1 - Note any discrepancies between the field reference doc and actual database schema — update doc accordingly - Demo to supervisor: SchemaInspector and SQLDiscovery running against real SQL Server instance - Write Week 9 status update; update GitHub board for Week 10 | Live SQL Server test passed; WMS Field Reference doc updated |

## Week 9 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| DBConnector Class | pyodbc wrapper with parameterized queries, context manager, 4 DB profiles | Intern → Supervisor |
| SchemaInspector Class | INFORMATION_SCHEMA-based introspection; column types, PKs, FKs, sample values | Intern; tested on SQLite |
| SQLNormalizer | SQL table schema → ParsedSchema bridge; integration tested with SchemaMapper | Intern → Supervisor |
| SQLDiscovery Module | CLI for table/view selection; stores SQLSourceConfig with join/filter support | Intern; live demo |
| WMS Field Reference Update | Field reference doc corrected against actual SQL Server schema where needed | Intern |
| Week 9 Status Update | Written summary; live SQL Server test results documented | Intern → Supervisor |

⚠ SQL Security Reminder All SQL executed by generated scripts must use parameterized queries — no f-string or string concatenation SQL construction anywhere in the codebase. This applies to both the agent itself and the scripts it generates. Flag any instance of string-built SQL immediately during code review; it is a critical defect regardless of context.

# Week 10 — SQL Query Builder & Code Generation  (Hrs 361–400)

The intern builds the SQL-specific code generation layer: LLM-assisted SELECT query construction from confirmed field mappings, INSERT/UPDATE logic for push operations, and Jinja2 templates for the generated sync scripts.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 46 | 8 hrs | LLM-Assisted SELECT Builder | - Build SQLQueryBuilder class: given SQLSourceConfig + confirmed FieldMapping, generates a parameterized SELECT statement that extracts exactly the mapped source columns - Use LLM to assist with column aliasing: if source column is ITEM_NO and WMS field is wms_part_number, the generated SELECT should alias it: SELECT ITEM_NO AS wms_part_number - Handle JOIN clause generation: if user specified a join in SQLSourceConfig, include it correctly with proper ON condition - Handle filter clause: WHERE conditions (e.g., only active items, only open orders) passed through safely as parameterized predicates - Write tests: 5 different SQLSourceConfig inputs → verify generated SELECT is syntactically correct using SQLite execution | SQLQueryBuilder generating correct parameterized SELECT for 5 test cases |
| Tue — Day 47 | 8 hrs | INSERT / UPSERT Builder | - Build push-direction query builder: generates parameterized INSERT or UPSERT (MERGE on SQL Server, INSERT ... ON CONFLICT on PostgreSQL) from WMS export data - UPSERT is preferred over INSERT for idempotency — research SQL Server MERGE syntax and implement a template for it - Handle batch inserts: generated script should batch records into configurable chunk sizes (default 500 rows) to avoid transaction log bloat - Write tests: push FieldMapping → verify generated MERGE statement is valid SQL using SQLite equivalent (INSERT OR REPLACE) - Document the MERGE pattern in the developer handoff doc — it is non-obvious and customers ask about it | UPSERT/MERGE builder generating valid batch-insert SQL |
| Wed — Day 48 | 8 hrs | SQL Pull Template (sql_pull.py.j2) | - Implement Jinja2 template for SQL pull script: connect → execute SELECT → iterate rows → transform types → write to WMS import format (CSV or JSON) - Generated script must include: connection retry on timeout (3 attempts, 5-second backoff), row count logging, configurable batch size for large result sets - Add delta/incremental pull support: generated script accepts --since <datetime> flag, appends WHERE last_modified > :since to the SELECT - Test: generate pull script from SQLite fixture → run it → confirm WMS-formatted output is identical to what a manual export would produce - Add --dry-run flag (same pattern as REST scripts) | SQL pull template generating executable script with delta support |
| Thu — Day 49 | 8 hrs | SQL Push Template (sql_push.py.j2) | - Implement Jinja2 template for SQL push script: read WMS export → validate required columns present → connect → batch UPSERT - Generated script must include: transaction wrapping (COMMIT on success, ROLLBACK on failure), per-batch error logging, dead-letter file for failed batches - Add pre-push validation: before executing any writes, run a dry-run SELECT to confirm target table exists and schema matches expected columns - Test: generate push script → run against SQLite fixture → confirm rows inserted correctly and rollback works on injected failure - Ensure generated scripts are compatible with both SQL Server and the fallback DBs (MySQL, PostgreSQL) via SQLAlchemy dialect | SQL push template with transactions, dead-letter, and pre-push validation |
| Fri — Day 50 | 8 hrs | Full SQL Pipeline Test | - Run full SQL pipeline end-to-end: connect → inspect → discover → normalize → map → confirm → generate pull + push scripts → execute both - Test against SQLite fixture (CI-safe) and against Modula WMS SQL Server test instance (live) - Measure time-to-integration for SQL path — record alongside REST and file metrics - Write Week 10 status update; update time-to-integration comparison table across all three methods - Update GitHub board for Week 11 | Full SQL pipeline working on SQLite and live SQL Server; metrics recorded |

## Week 10 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| SQLQueryBuilder | LLM-assisted SELECT with aliasing, JOIN, filter, parameterized predicates | Intern; 5 tests passing |
| UPSERT/MERGE Builder | Batch INSERT/MERGE generator for SQL Server and fallback DB dialects | Intern; tested on SQLite |
| sql_pull.py.j2 Template | Pull script with delta support, retry, batch size, dry-run flag | Intern; live SQL Server test |
| sql_push.py.j2 Template | Push script with transaction wrap, dead-letter, pre-push schema validation | Intern; tested on SQLite |
| Time-to-Integration Table | Comparison: file vs REST vs SQL — median minutes from input to working scripts | Intern → Supervisor |
| Week 10 Status Update | Written summary; SQL pipeline live test results | Intern → Supervisor |

# Week 11 — Bidirectional Sync Engine & Phase 3 Code Review  (Hrs 401–440)

The intern builds the sync engine — the layer above the individual pull/push scripts that coordinates bidirectional data exchange, detects changes, handles conflicts, and maintains a transaction log. This is the most architecturally complex component of the project.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 51 | 8 hrs | Change Detection Strategies | - Research and implement three change detection strategies as interchangeable classes under a common ChangeDetector interface: - 1. Timestamp-based: query WHERE last_modified > last_sync_time (requires a last_modified column in source) - 2. Checksum-based: hash each row's key fields, compare to stored hashes from last run, flag rows where hash changed - 3. Full-diff: fetch all current rows, compare to snapshot from previous run (expensive — only for small tables) - Store last_sync_time and row checksums in a local SQLite state database (sync_state.db) — one per configured integration - Write tests: each strategy correctly identifies added, modified, and deleted rows in a simulated change set | Three ChangeDetector strategies passing tests; sync_state.db pattern established |
| Tue — Day 52 | 8 hrs | Conflict Handling Rules | - Define ConflictPolicy enum: SOURCE_WINS (overwrite target), TARGET_WINS (skip if target has newer record), MANUAL_REVIEW (write to conflict log, do not apply) - Build ConflictResolver: given two versions of a record (source and target), applies the configured ConflictPolicy - For MANUAL_REVIEW: write conflicting records as JSON pairs to conflicts_{timestamp}.json — same pattern as dead-letter files - Add last_modified timestamp comparison for SOURCE_WINS and TARGET_WINS — requires both systems to have reliable timestamps - Configure ConflictPolicy per integration in the YAML config file generated alongside scripts | ConflictResolver applying all three policies correctly; conflict log file generated |
| Wed — Day 53 | 8 hrs | Transaction Log | - Build SyncLogger: append-only transaction log written to sync_log_{integration_id}.jsonl — one JSON line per sync event - Log schema: {timestamp, integration_id, direction, records_detected, records_synced, records_failed, records_conflicted, duration_seconds, error (optional)} - Build a simple log reader CLI: python sync_log.py --integration <id> --last 10 — prints last N sync results in readable table format - Add log rotation: when log file exceeds 50MB, rotate to sync_log_{integration_id}_{date}.jsonl.gz and start new file - Write tests: SyncLogger produces valid JSONL; log reader parses it correctly after rotation | SyncLogger producing JSONL; log reader CLI working; rotation tested |
| Thu — Day 54 | 8 hrs | Sync Engine Assembly | - Wire ChangeDetector + ConflictResolver + SyncLogger into a SyncEngine class: orchestrates a full bidirectional sync cycle - SyncEngine.run() method: detect changes → resolve conflicts → apply changes (pull or push) → log result → update sync state - SyncEngine is integration-type agnostic: works with generated SQL scripts, REST scripts, or file scripts — it wraps them, not replaces them - Write integration test: simulate a 3-cycle sync with changes and conflicts — verify state, log, and conflict files are all correct - Add SyncEngine to the pipeline runner: python run_pipeline.py --sync enables sync mode after initial script generation | SyncEngine running 3-cycle integration test correctly |
| Fri — Day 55 | 8 hrs | Phase 3 Code Review & SQL Demo | - Full Phase 3 code review with supervisor: DBConnector, SchemaInspector, SQLNormalizer, SQLDiscovery, SQLQueryBuilder, MERGE builder, both SQL templates, SyncEngine, SyncLogger - Demo to supervisor: full SQL pipeline on live SQL Server — pull from WMS test instance, push sample data to a scratch table, run 2 sync cycles - Address all critical code review findings - Write Week 11 status update; confirm all three integration types are working - Update GitHub board for Week 12 (Agent Orchestration) | Code review complete; SQL demo accepted; all three integration types confirmed working |

## Week 11 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| ChangeDetector (3 strategies) | Timestamp, checksum, full-diff strategies; sync_state.db for state storage | Intern; integration tested |
| ConflictResolver | SOURCE_WINS / TARGET_WINS / MANUAL_REVIEW policies; conflict log file | Intern |
| SyncLogger + Log Reader | JSONL append-only log; CLI reader; 50MB rotation to gzip archive | Intern; tested |
| SyncEngine Class | Orchestrates full sync cycle; integration-type agnostic; 3-cycle test passing | Intern → Supervisor demo |
| Phase 3 Code Review | Completed with supervisor; all critical findings resolved | Intern + Supervisor |
| Week 11 Status Update | Written summary confirming all three integration types operational | Intern → Supervisor |

💡 Scope Management Note The SyncEngine is a sketch — it should be functional enough to demonstrate the concept and run in the test environment, but it is not production-hardened. Distributed locking, exactly-once delivery guarantees, and high-availability patterns are explicitly out of scope. Document these gaps in LIMITATIONS.md. The goal is a working, demonstrable prototype that the team can extend post-internship.

# Week 12 — Agent Orchestration & Unified Interface  (Hrs 441–480)

The intern unifies all three integration modules under a single agent interface — the primary deliverable that a Modula implementation engineer will actually use in the field. The interface guides the user from zero to a working integration without requiring them to understand which module is running underneath.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 56 | 8 hrs | Agent Architecture Design | - Design the unified agent flow: Welcome → Integration Type Detection → Type-Specific Input Wizard → Map & Confirm → Generate → Validate → Output Summary - Integration Type Detection: agent asks the user a short series of questions to determine which module to use (does the customer have an API? a shared database? file exports?) - Design as a state machine: each state has an input handler, a transition function, and a display function — clean separation of logic from presentation - Write the AgentState enum and AgentContext Pydantic model (carries all collected information through the wizard) - Review design with supervisor before building — 30-minute design discussion | Agent state machine design reviewed and approved by supervisor |
| Tue — Day 57 | 8 hrs | Input Wizard — Detection & Routing | - Implement the detection phase: 3–5 questions that reliably route to file, REST, or SQL module - Questions should be non-technical where possible — e.g., 'Does your ERP have a web API? (yes/no/unsure)' rather than 'Do you have an OpenAPI spec?' - Implement fallback: if user answers 'unsure', agent asks a follow-up that narrows down the answer - Build the routing logic: detection answers → IntegrationType enum → load appropriate module - Test: 10 different simulated user answer sequences — confirm all route to the correct module | Detection and routing working for all three integration types |
| Wed — Day 58 | 8 hrs | Input Wizard — Type-Specific Flows | - Implement File wizard: prompt for file path → run ingest() → display ParsedSchema summary → proceed to mapping - Implement REST wizard: prompt for base URL, auth type, auth credentials → optionally prompt for spec URL or raw JSON sample → run discovery → proceed to mapping - Implement SQL wizard: prompt for connection string or guided DSN builder (server, database, username, password) → test connection → run table discovery → proceed to mapping - All three wizards converge at the same mapping confirmation step — confirm this works by running all three end-to-end - Add input validation at each wizard step: file must exist, URL must be reachable, DB connection must succeed before advancing | All three type-specific wizards working and converging at mapping step |
| Thu — Day 59 | 8 hrs | Output Package & Session Resume | - Define standard output package structure: output/{integration_name}/{timestamp}/README.md, mapping.json, generated_scripts/, config.yaml, validation_report.txt - Auto-generate README.md inside each output package: explains what was generated, how to configure and run the scripts, what the scheduler scaffold does - Add session save/resume: agent saves AgentContext to a session.json file after each completed step — if interrupted, user can run python agent.py --resume session.json to continue from last completed step - Test session resume: interrupt agent at each of the 5 phases, confirm resume picks up correctly - Update developer handoff doc with output package structure | Output package with auto-README; session resume working at all 5 phases |
| Fri — Day 60 | 8 hrs | User Guide & Interface Polish | - Write the User Guide: a step-by-step document for a Modula implementation engineer who has never used the agent before — not a developer, not a programmer - User guide covers: running the agent, answering the wizard questions, reviewing and confirming field mappings, where to find the output, how to deploy the generated scripts to a customer environment - Polish the CLI: add color output (colorama or rich library), clear progress indicators, friendly error messages that suggest fixes rather than printing stack traces - Write Week 12 status update; update GitHub board for Week 13 - Send draft User Guide to supervisor for feedback | User guide drafted; CLI polished; supervisor feedback requested on user guide |

## Week 12 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| Unified Agent Interface | State-machine CLI wizard routing to all 3 modules; converges at shared mapping step | Intern → Supervisor review |
| Session Save/Resume | AgentContext saved to session.json; --resume flag continues from last completed step | Intern; tested at 5 phases |
| Output Package Structure | Standard folder with auto-generated README, scripts, config, validation report | Intern |
| User Guide (Draft) | Step-by-step guide for non-developer implementation engineers; sent for review | Intern → Supervisor feedback |
| CLI Polish | Color output, progress indicators, user-friendly error messages (no raw tracebacks) | Intern |
| Week 12 Status Update | Written summary; agent running all 3 integration types through unified interface | Intern → Supervisor |

# Week 13 — Demo, Documentation & Handoff  (Hrs 481–520)

The final week. The intern incorporates feedback from Week 12, prepares and delivers the end-to-end demonstration using real anonymized customer data, completes all handoff documentation, and presents findings and a forward-looking roadmap to the Software Implementation team.

## Day-by-Day Schedule

| Day | Hrs | Theme | Tasks | End-of-Day Check |
| --- | --- | --- | --- | --- |
| Mon — Day 61 | 8 hrs | Feedback Incorporation | - Review supervisor feedback on User Guide from Week 12 — revise and finalize - Address any outstanding issues from Phase 3 code review - Update LIMITATIONS.md with any new edge cases discovered during Week 12 testing - Finalize all docstrings, README sections, and inline comments across the entire codebase - Run full test suite — confirm all tests pass on a clean environment (delete venv, reinstall from requirements.txt, run tests) | All feedback incorporated; test suite passing on clean install |
| Tue — Day 62 | 8 hrs | Demo Preparation | - Select demo scenarios (with supervisor): one file-based, one REST API, one SQL — using real anonymized customer data where possible - Rehearse full demo end-to-end twice — time it (target: under 20 minutes for all three integration types) - Prepare demo fallback: if live agent fails during presentation, have pre-recorded screen capture as backup - Prepare the roadmap slide deck: 5–8 slides covering architecture overview, what was built, metrics (time-to-integration, mapping accuracy), known limitations, and recommended next steps - Practice presenting the roadmap — keep it under 10 minutes | Demo rehearsed twice; roadmap deck drafted; fallback recording ready |
| Wed — Day 63 | 8 hrs | Developer Handoff Package | - Finalize developer handoff doc: architecture overview, module descriptions, how to add a new integration type, how to update LLM prompts, how to add a new ERP mock profile, known limitations, recommended extensions - Write environment setup guide: exact steps to install all dependencies from a bare Windows or Ubuntu machine — test on a second machine or VM if possible - Tag a v1.0.0 release on GitHub: clean commit, release notes listing all modules and deliverables - Create a final requirements.txt and optionally a Dockerfile for reproducible environment - Deliver complete handoff package to supervisor for review: handoff doc + user guide + GitHub link | Handoff package delivered to supervisor; v1.0.0 tagged on GitHub |
| Thu — Day 64 | 8 hrs | Final Presentation | - Deliver live demo to Software Implementation team: all three integration types, agent wizard, generated script output, sync engine overview - Present roadmap deck: architecture decisions, metrics, limitations, recommended next steps - Q&A with team — document any questions or feedback that surfaces new feature ideas or gaps - Record all post-presentation feedback in a final-feedback.md file committed to repo - Supervisor delivers verbal internship performance feedback to intern | Final presentation delivered; team feedback documented |
| Fri — Day 65 | 8 hrs | Wrap-Up & Knowledge Transfer | - Final 1:1 with supervisor: review internship outcomes against success criteria from the project outline - Walk supervisor through codebase live — any module that needs verbal explanation should get a screen-share walkthrough and recorded loom/Teams video if possible - Complete internship retrospective: personal reflection on technical growth, what the intern would do differently, what advice they would give the next intern on this project - Ensure all credentials, API keys, and connection strings are removed from the repo and stored in the team's secrets manager - Intern's last commit: update README with 'Internship completed [date] — project status and next steps for continuation' | Knowledge transfer complete; repo clean of secrets; final retrospective written |

## Week 13 Deliverables

| Deliverable | Definition of Done | Owner / Reviewer |
| --- | --- | --- |
| Final User Guide | Revised based on supervisor feedback; complete step-by-step for implementation engineers | Intern → Final version |
| Developer Handoff Doc | Architecture, module guide, extension instructions, ERP profiles, limitations | Intern → Supervisor |
| Environment Setup Guide | Bare-machine install steps tested on a second environment | Intern |
| v1.0.0 GitHub Release | Tagged release with release notes; clean requirements.txt; optional Dockerfile | Intern |
| Final Presentation | Live demo (3 integration types) + roadmap deck delivered to Software team | Intern → Full team |
| Roadmap Deck | 5–8 slides: architecture, metrics, limitations, recommended next steps | Intern → Full team |
| Final Retrospective | Personal reflection committed to repo; internship outcomes vs. success criteria reviewed | Intern + Supervisor |
| Knowledge Transfer | Live codebase walkthrough with supervisor; optional recorded video | Intern → Supervisor |

✅ Internship Completion Criteria The internship is considered complete and successful when all of the following are true: • All three integration types (file, REST, SQL) working through unified agent interface • Final demo delivered to Software Implementation team • Developer handoff doc, user guide, and environment setup guide finalized • v1.0.0 tagged on GitHub with clean test suite • No credentials or secrets remaining in repository • Supervisor has confirmed handoff package is sufficient to continue the project without the intern

📋 Recommended Next Steps (Post-Internship Roadmap) The following are the highest-priority extensions for whoever continues this project: 1. Salesforce Work Order integration — push/pull WMS events using Salesforce REST API (aligns with existing Modula SF template work) 2. Web UI — replace CLI wizard with a browser interface accessible to non-developer implementation staff 3. Expanded ERP mock library — add Epicor, Infor CloudSuite, and Sage 100 profiles 4. Auto-test harness — agent generates both the middleware and a test suite for it 5. Customer self-service portal — long-term: customers upload files and receive integration packages directly

Document prepared by: Software Implementation Team  |  Modula USA  |  May 2026